## Sheet1
S.No. | Main Task | Task breakdown | Dev estimate(hrs)
1 | Creating overall navigation | Creating overall flow of screens between Main page, Statement B, Statement C, Statement D | 8
2 | Adding new LM-21 | Adding new LM-21 | 8
3 | Amending an LM-21 | Amending an LM-21 | 8
4 | Form Validation | Validation for Starting new form,Never filed, selecting an existing form | 8
5 | Page 1- Prefill | Fetching prefilled data from database | 8
|  | Displaying the data from db to the specific fields on screen | 8
6 | Page 1- Signature | Signature | 8
7 | Page 1- Javascript Validations | Validations for Item 1 | 8
|  | Validations for Item 2 and 17 | 8
8 | Page 1- Fields, Look and Feel | Creating all the fields, look and feel Item 1 | 8
|  | Creating all the fields, look and feel Item 2 and 17 | 8
|  | Consistent Styling page 1 | 8
9 | Statement B- Javascript Validations | Validations for item 5.a | 8
|  | Validations for item 5.b and 6 | 8
10 | Statement B- Employer Name Lookup | Fetching search results on click of employer search | 8
|  | Adding new employer and employer not found functionality | 8
|  | Employer - fill/populate item 5.a | 8
11 | Statement B- Fields, Look and Feel | Creating the fields,look and feel under statement B | 8
|  | Consistent Styling Statement B | 8
12 | Statement B- Add Additional Employer | Creating the fields under 5.a. | 8
|  | Validations for item 5.a | 8
13 | Statement B- Delete Employer | Deleting the employer details | 8
14 | Statement C- Javascript Validations | Validations for item 7 | 8
|  | Validations for item 8,9,10,11,12,13,14 | 8
15 | Statement C- Fields, Look and Feel | creating all the fields, look and feel | 8
|  | Consistent Styling Statement C | 8
16 | Statement C- Add Additional Officers and Employers | Add additional Officers and employees | 8
17 | Statement C- Delete Additional Officers and Employers | Delete Additional Officers and employees | 8
18 | Schedule D- Javascript Validations | Validations for 15 a,b,c,d,e and 16 | 8
19 | Schedule D- Fields, Look and Feel | Creating all the fields, look and feel | 8
|  | Consistent Styling Statement D | 8
20 | Schedule D- Add Additional Reportable Activities | Add Additional Reportable Activities | 8
21 | Schedule D- Delete Additional Reportable Activities | Delete Additional Reportable Activities | 8
22 | Schedule D- Employer Name Lookup | Fetching search results on click of employer search | 8
|  | Adding new employer and employer not found functionality | 8
|  | Employer - fill/populate item 15.a,b,c | 8
23 | Validation Summary | Listing validation summary for Main page and Statement B | 8
|  | Listing validation summary for Statement c and Statement D | 8
24 | Access key tab | Implement Access key for LM-21 | 8
|  | Reset Access key | 8
25 | Save functionality | Saves all the changes of the form and it will be enabled only if the filer makes any changes | 8
26 | Add attachments functionality | add attachments functionality | 8
27 | Validate functionality | Validate button functionality | 8
28 | Print functionality | Print functionality | 8
29 | Form instructions, help | Form instructions, help functionality | 8
30 | Save and calculate | Save and calculate functionality | 8
31 | Submit button | Submit functionality | 8
Total Hours |  |  | 376